## Plan
Plan ID | Plan name | Date of export
tpwD5oUwaEOyJOwRgEAlmckAAcrp | R26-IT-118 | 2026-10-13

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
dGQX8oSgZUC1UDoteFlAockALZ8Q | Report monthly status | 4. System Development — Disease Detection |  | Not started | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-10-08 |  |  | true
0jD4mQMw9UyesHKEPM8ilckAKh3G | Report monthly status | 4. System Development — Disease Detection |  | Completed | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-09-08 |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
eQO25QVO_kqGm47cxW_r9ckABNmU | Report monthly status | 4. System Development — Disease Detection |  | Completed | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 | 2026-08-08 |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
Yf4OssUZzUuRY-M_RM_cHskAMa7l | Report monthly status | 4. System Development — Disease Detection |  | Completed | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 | 2026-07-08 |  |  | false | 2026-10-13 | MIURANGA W A R it22209320
1HB9ntvkqk-8_R2RheSN3MkAOUd6 | Report monthly status | 4. System Development — Disease Detection |  | Completed | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-06-08 |  |  | false | 2026-10-13 | MIURANGA W A R it22209320
MIYmCcyhgUWZ_pWeBMlgvskAH7SA | Report monthly status | 4. System Development — Disease Detection |  | Completed | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-04-29 | 2026-06-26 |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
u0fgWxTZPkGXq-Z2Wbz-pskAFPZi | Summarize project results and lessons learned | 11. PP1 — Progress Presentation 1 |  | Completed | Medium | PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-04-29 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320
9YcC9HcqI0WKWk7AvggylckAI0D3 | Conduct team performance reviews | 4. System Development — Disease Detection |  | Not started | Medium | GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 | 2030-09-08 |  |  | false
Vh007uk9yE-xTElFZ7dT8skADENp | Conduct team performance reviews | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 | 2026-07-18 |  |  | false | 2026-10-13 | MIURANGA W A R it22209320
vfeXmboQ_UamovDn-RXJx8kAGdgB | Conduct team performance reviews | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2027-09-08 |  |  | false | 2026-10-13 | MIURANGA W A R it22209320
9sh_lIm0MU-OBCMeUkpowckAANkt | Conduct team performance reviews | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-09-08 |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
ijtAq0pG6ESFnPlhdttNQMkAPIAD | Conduct team performance reviews | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-04-29 | 2026-09-26 |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
QVfw8Kn48U22K9u248gidckAH_v3 | Research Topic Finalization | 1. Project Initialization |  | Completed | Important | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-05-13 | 2025-11-01 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Finalize research title Confirm group members Confirm supervisor Prepare problem statement
hWBjiXu5kkCFqbSJffT7FMkAC66p | Research Proposal Creation | 1. Project Initialization |  | Completed | Important | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-02-14 | 2026-02-12 |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Identify research objectives Conduct initial literature review Identify research gapPrepare proposed solution Prepare initial project documentation
b1T4wnoEGEqrwPHy-oPHxMkAEdyW | Dataset Collection | 2. System Planning & Dataset Preparation |  | Completed | Urgent | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-04-01 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Tea disease dataset collection Tea grading dataset collection Weather dataset collection Labor management Health Data collection
GB5dCDapvkyIROE1SJuYFMkAJraN | System Planning and Setup | 2. System Planning & Dataset Preparation |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-04-10 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320
Jvs2vxKahUinnAMg-cKyXMkAHqQC | Create GitHub repository | 2. System Planning & Dataset Preparation |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-04-11 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320
cUfng4-1oUuA4f7Yeb99vskALXH4 | AI Model Development - Tea Disease Detection System | 2. System Planning & Dataset Preparation |  | Completed | Important | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-04-17 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | CNN implementation YOLO Development Image preprocessing Train disease detection model Accuracy testingF1 score evaluation Prediction testing Model optimization
NvFxzavu4ECGmgkCD4x_1skALQ7k | Literature Review | 1. Project Initialization |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-02-19 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Collect research papers Study tea industry problem Identify research gap Prepare references
diJTncqHb0WwAC2Q8TD9VckAHZ5- | UI Wireframe Design | 3. Frontend and Backend Setup |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-05-13 | 2026-04-19 |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Create dashboard wireframe Design login page Design analytics pages Review UI structure
0c49YPI27kOpZ_Uhdjs_2MkAEtE8 | Frontend Project Setup | 3. Frontend and Backend Setup |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 | 2026-04-21 |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Setup React projectInstall dependencies Configure Tailwind CSS Setup folder structure
Fy7YaYKT1EqXjeV51FRGm8kAJcNe | Backend Project Setup | 3. Frontend and Backend Setup |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Setup Node.js backend Configure Express server Setup API structure Configure middleware
ulxL1inMukiUTudFyfLEAskAOLUA | Database Configuration | 3. Frontend and Backend Setup |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Setup MongoDBConfigure database connection Create collectionsTest database operations
4gajoxcfPk6snQlmO6TjeckABVz6 | Authentication System Setup | 3. Frontend and Backend Setup |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Setup JWT authentication Configure login system Configure register system Test authentication APIs
D7KmFTeapUipd4v7uW_1mckAIe3y | Train ML Model | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Train tea disease detection modelOptimize CNN and YOLO models Evaluate model accuracy Improve F1 Score
mAwHDgH6yEOg46Y_JngiA8kAMJ-D | Backend Connection | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Connect AI model with backend Configure FastAPI endpoints Connect MongoDB Test API responses
3PpHaS6qyEuTKIy8Bf7P4ckACWpW | Frontend Connection | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Connect frontend image upload Display prediction results Add confidence scores Test frontend integration
iJLIr-C7UESXqOS5lNbhSckAOl-7 | Tea Leaf & Non-Tea Leaf Identification | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Detect tea leaf images Identify non-tea leaf images Improve classification accuracy Test prediction outputs
2HpaJRldo0eF083eD2dcF8kAM7X5 | YOLO Integration | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Connect YOLO model Configure object detection Detect tea diseases using YOLO Test live prediction system
65iayVmXDkGqqFO9wvQoSMkACwB0 | PP1 Presentation Create | 11. PP1 — Progress Presentation 1 |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320
231PV_EWdUibOZj_7qPSN8kAOCx5 | Check List 1 README Github | 11. PP1 — Progress Presentation 1 |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320
RVqjqBkD60iB-4cCLino3ckAJLWV | PP1 Presentation | 11. PP1 — Progress Presentation 1 |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320
4z8vJqCdnEGtG9q6p4T-lskAJgji | Disease Detection System | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Detect tea leaf diseasesImprove disease prediction Add disease confidence scoresOptimize disease classification
B3z-QXxT6UGWEy7RNMF4PskABIth | Full System Integration | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Integrate frontend and backendIntegrate AI prediction system Test complete workflow Fix integration issues
oAMlPowAKEe_xnpg2Rj0QckAKG5u | Labor Management and Welfare Planning | 2. System Planning & Dataset Preparation |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Analyze labor management and worker welfare requirements Design AI-based workforce management workflow Identify worker monitoring and task allocation features Prepare system planning documentation
UsEIvuAheU2rTL6LwfhOvMkAIT6y | Worker Registration and Monitoring | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | MIURANGA W A R it22209320 |  |  |  | Design worker management system Create worker data structures and monitoring workflow Implement worker profile and status management Test worker management functionality
__lyi8NTY0u7dMVr-YTkhMkALGwf | AI-Based Health Risk Prediction | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Integrate worker health prediction model Process manually entered Heart Rate and SpO₂ health data Generate worker health risk predictions Test prediction workflow and model responses
MfzOHHFlkkuPJpomC6yU1ckAP-Se | Worker Registration and Monitoring | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-05-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Design worker management system Create worker data structures and monitoring workflow Implement worker profile and status management Test worker management functionality
kswIc-pQz0KhugRirV8rPMkAESnW | Smart Task Allocation System | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Develop AI-based task allocation logic Create risk-based task recommendation process Assign suitable tasks according to worker health condition and skill category Improve workforce allocation efficiency
EKJrK6-gwE2m4BJU_cPk9MkAD9Hk | Backend and Database Integration | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Connect labor management module with backend Configure MongoDB collections and APIs Process manual health data inputs Verify backend communication and database operations
e2c456CRqE-lo4ye7gv1wMkABz2P | Frontend Integration and Dashboard | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Connect labor management frontend dashboard Add worker monitoring and task allocation UI Display worker health predictions and analytics Test frontend workflow and user interactions
28S1cp7gZ0qC7IdRvYWoTckAJbUa | Future IoT Integration Planning | 4. System Development — Disease Detection |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-05-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Plan real-time IoT device integration for health monitoring Prepare system workflow for automated data collection Design future real-time monitoring process
FFY07VazPUynEmV6owPbbMkALF2n | Conduct Initial Research Meeting | 1. Project Initialization |  | Completed | Urgent | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 |  | 2026-02-24 |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Discussed the research idea, project scope, and responsibilities among team members.
5D7b3CnXo0--E9QX3crzSMkAMvij | Identify Research Gap | 1. Project Initialization |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-10-13 |  | 2026-02-13 |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Identified areas where existing tea estate management approaches could be improved.
8P82YWpsQUeiHRazsCl-bckAHXnI | Discuss Proposal with Supervisor | 1. Project Initialization |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320
0wyngspXmUCbNpt21vbSq8kAKQXv | Identify Dataset Sources | 2. System Planning & Dataset Preparation |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-03-31 | 2026-03-01 |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Identified relevant data sources for disease detection, labour management, weather intelligence and tea grading. Copy task and note
uso7or0MbUKlXlwZSrDp4skAJL_H | Prepare System Design Diagrams | 2. System Planning & Dataset Preparation |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-03-31 | 2026-03-09 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Prepared worker-related data for labour management and health prediction. Copy task and note
hRB3N5j3jU6V4gTeezcRZ8kAKTGS | Create Dashboard Layout | 3. Frontend and Backend Setup |  | Completed | Medium | GUNASEKARA G N D it22279620;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-10-10 | 2026-04-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Prepared the shared dashboard layout for the integrated system. Copy task and note
rrlrj6XfVE28-W3hWm3I_ckAIAwT | Test Frontend and Backend Connection | 3. Frontend and Backend Setup |  | Completed | Important | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-04-15 | 2026-04-10 |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Checked frontend requests, backend responses and connection behaviour. Copy task and note
sF86Pm2d9UmRf34turONDskAPfw1 | Research Tea Leaf Disease Detection | 4. System Development — Disease Detection |  | Completed | Medium | MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Reviewed image-based methods for identifying tea leaf diseases. Copy task and note
esgNr9KxPEaRosJSFH_xZskAA2hZ | Research Labour Management Requirements | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Reviewed workforce management and worker welfare challenges in tea estates.
QeHSdyKZIEGlkEROGPg978kADtNr | Prepare Worker Health Dataset | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-03-31 | 2026-03-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Prepared worker health data for the prediction component.
g87yy0ub6EOGN0F5FR8RPskAKQzi | Develop Worker Health Prediction Model | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-04-30 | 2026-03-25 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Developed and evaluated the worker health prediction approach.
kNdA2oBZ9kO-EWEa6I-oAskAKNUx | Develop Worker Profile Management | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-04-15 | 2026-04-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Prepared functionality for managing worker information.
V5PYC2TYCEqpaw5uTIDbM8kAPOvc | Develop Task Allocation Workflow | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-04-30 | 2026-04-21 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Developed the workflow for assigning tasks to workers.
FwxEUA697UCacU_xIRsDl8kAG_Bl | Implement Attendance and Productivity Features | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-06-15 | 2026-06-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Developed attendance and productivity monitoring features.
PeozywJuZkWVKAsZtoN3w8kAKbS3 | Integrate Health Monitoring Data | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-07-20 | 2026-07-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Connected available worker health monitoring data to the module.
4rM_QRf3Qka9EcLT9xH1hckAPYE4 | Test Labour Management Module | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-08-15 | 2026-08-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Tested worker management, task allocation and health prediction functionality.
aZetjI1FTUOCjrdWnOsVoMkAK5Tt | Prepare PP2 Demonstration | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-08-30 | 2026-08-21 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Prepared the labour management demonstration for PP2.
g3mDxw4SsUijdK6JdjiFfMkAGOWF | Update Labour Documentation | 5. System Development — Labour Management |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-10-10 | 2026-09-01 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Updated technical documentation and available testing evidence.
Dc6Vr1SFUkCIBp7g6kkGbckAAz9a | Final Labour Module Verification | 5. System Development — Labour Management |  | Completed | Important | GUNASEKARA L.M.N.P it22267986 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 | 2026-10-14 | 2026-10-10 |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Verify the current module and prepare evidence for the final checklist.
EfsmJTEOjkeTOyrWOXDOt8kAPaSG | Research Weather Intelligence Requirements | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | true | [5 empty] | Identified the weather monitoring and forecasting needs of tea estates.
oye7HXWx202u7ztxhKAuKskADdDi | Collect and Prepare Weather Dataset | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-03-31 | 2026-03-01 |  | true | [5 empty] | Prepared temperature, humidity and rainfall data for model development.
GQvI8HLUVkaPc8XMs1yQzckAOedh | Train Weather Prediction Models | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-04-15 | 2026-04-01 |  | true | [5 empty] | Developed models for weather forecasting and tea disease risk prediction.
qRvE3wll_UuGzGbUD-4IkMkAMk3p | Develop Regional Weather Forecasting | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-05-15 | 2026-05-01 |  | true | [5 empty] | Prepared regional forecasting functionality for supported tea-growing areas.
zDFr1sC2_UGMd0V81IEL08kAJtNU | Develop Weather API | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-06-15 | 2026-06-01 |  | true | [5 empty] | Prepared API endpoints for weather readings and prediction results.
AB_69EkMf02eXH6jEKaNHskAGgUn | Integrate Weather Service | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-06-30 | 2026-06-15 |  | true | [5 empty] | Connected the weather service to the main application.
ZJnv3xHMLUe2ihXYdMQr98kACxOb | Implement Weather Risk Alerts | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-07-30 | 2026-07-01 |  | true | [5 empty] | Implemented alerts for supported weather and disease-risk conditions.
WUOeQUy5r0eGXwl0j3QHf8kAAO90 | Test Weather Predictions | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-07-31 | 2026-07-21 |  | true | [5 empty] | Checked forecast outputs and available prediction results.
1lkiVH_ouk2Y_2cURT6_8ckAHckI | Prepare PP2 Demonstration | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-08-20 | 2026-08-01 |  | true | [5 empty] | Prepared the weather intelligence demonstration for PP2.
ehy5WDxXNUGUQhk-eaPul8kAKKIk | Update Weather Documentation | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-09-16 | 2026-09-01 |  | true | [5 empty] | Updated implementation details and supporting evidence.
Q68Lh8WYLUu6XvQJsaPrtckAOhhI | Final Weather Module Verification | 6. System Development — Weather Intelligence |  | Not started | Medium | GUNASEKARA G N D it22279620;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-10-21 | 2026-10-01 |  | false | [5 empty] | Verify current weather functionality and prepare final checklist evidence.
SL_NArCGMUKcWXfqPHXtgskALqTt | Research Tea Grading Requirements | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Reviewed the requirements for automated tea quality grading.
nc5KMuZvGUypP1_25jG_C8kAGHus | Prepare Tea Grading Dataset | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-03-15 | 2026-03-01 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Organized tea sample images and the supported grade categories.
i1cGSsbcA0OImT4s6KN-lckANDgB | Preprocess Tea Images | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-04-15 | 2026-04-01 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Prepared tea images for model training and evaluation.
ghpkzRLOKU6IjfqseDjckMkAKd9H | Train Tea Grading Model | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-04-30 | 2026-04-15 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Trained the selected deep learning model for tea grading.
wLIxLsxyO0Wf0aEMjgluHMkANugB | Evaluate Grading Model | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-05-30 | 2026-05-16 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Evaluated grading predictions using the available test data.
UnGIPv2KgUadE26sV9v6GckAIEUH | Deploy Grading Model | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-06-15 | 2026-06-01 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Configured access to the grading inference service.
yX-XQDAVSEKTfrnGq5Aiu8kAHGNl | Prepare PP2 Demonstration | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-10-31 | 2026-08-11 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Prepared the tea grading demonstration for PP2.
0uf84wuJR0Wu5L_IxUzkd8kAAtY9 | Update Grading Documentation | 7. System Development — Tea Sorting & Grading |  | Completed | Medium | PATHIRANA I M it22282668 | PATHIRANA I M it22282668 | 2026-10-13 |  | 2026-09-01 |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Updated implementation details and available test evidence.
0ulLgPowT02i0xoliTmKN8kAArWo | Final Grading Module Verification | 7. System Development — Tea Sorting & Grading |  | In progress | Medium | PATHIRANA I M it22282668 | PATHIRANA I M it22282668 | 2026-10-13 | 2026-10-19 | 2026-10-01 |  | false | [5 empty] | Verify current grading functionality and prepare final checklist evidence.
Btb1AWF_0U2oZFtdVkhk_8kAFk3W | Prepare Model Training Environment | 8. Machine Learning Model Development |  | Completed | Medium | MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Configured the required environment and libraries for model training.
hXpM9_zp-U-ZaL37-MUsXckAAUw1 | Preprocess Training Data | 8. Machine Learning Model Development |  | Completed | Medium | MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Prepared training data for use by the selected models.
0e-rW83XdkyjAMKZ0C4M9MkAIr3r | Split Training and Validation Data | 8. Machine Learning Model Development |  | Completed | Medium | MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Divided available data for training and model evaluation.
GdhDrvU-0UWv-dGAwq7pJ8kAFroe | Train Component Models | 8. Machine Learning Model Development |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Trained the machine learning models for the relevant components.
r-9BWDRDv0qXHKo9637XiskAJ1Ie | Tune Model Parameters | 8. Machine Learning Model Development |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Adjusted model parameters to investigate performance improvements.
Qh8JsE6gs0WK4xxLirr6sMkAAFuH | Evaluate Model Performance | 8. Machine Learning Model Development |  | Completed | Medium | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Evaluated models using appropriate metrics and test data.
T2TpWz-nEUaaiN5V7BoJ5MkAPG_j | Deploy Model APIs | 8. Machine Learning Model Development |  | Completed | Medium | PATHIRANA I M it22282668;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Configured API access to the deployed models.
KuzyE9O9JEGp-86WP4Df6ckAJjrX | Test Model Predictions | 8. Machine Learning Model Development |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | PATHIRANA I M it22282668 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Tested model outputs using suitable input samples.
eZ2ohrMBuU2W9K_W8dybM8kAN_a3 | Integrate Disease Detection Module | 9. System Integration |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Connected the disease detection component to the main system.
b_L7h-WbbUqcMnlfFgLHJMkANXTi | Integrate Labour Management Module | 9. System Integration |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Connected the labour management component to the main system.
qaxr_QSU5k6cSEKSGtnPqMkAHV4s | Integrate Weather Module | 9. System Integration |  | Completed | Medium | GUNASEKARA G N D it22279620 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Connected the weather intelligence component to the main system.
85aJSc4spUKmwEbEn2OfGMkAG6bm | Integrate Tea Grading Module | 9. System Integration |  | Completed | Medium | PATHIRANA I M it22282668 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Connected the tea grading component to the main system.
BRAZAWWGxkKtn1mR1BpzBskADm0s | Verify Frontend and Backend Communication | 9. System Integration |  | Completed | Important | GUNASEKARA G N D it22279620;PATHIRANA I M it22282668;GUNASEKARA L.M.N.P it22267986;MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Checked communication between the user interface and backend services.
xWRBlPjLA0CGjqaON4NB88kAOwN- | Prepare Functional Test Cases | 10. Testing and Validation |  | Completed | Medium | PATHIRANA I M it22282668 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | PATHIRANA I M it22282668 |  |  |  | Prepared test cases for the main system functions.
qriOGYtvCkKVZFZWMkeEUMkADzIg | Test Individual Components | 10. Testing and Validation |  | Completed | Medium | GUNASEKARA L.M.N.P it22267986 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986 |  |  |  | Tested the functions of each individual component.
YN0n5j77kEinRGbdlRUHockALMST | Test Valid and Invalid Inputs | 10. Testing and Validation |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Checked system behaviour with valid and invalid inputs.
BOU1W79_VkOMe2Wu5EpkjskAMJDm | Verify ML Model Predictions | 10. Testing and Validation |  | Completed | Medium | GUNASEKARA G N D it22279620 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Checked model outputs against the available test samples.
tkfVjlSHBk2Qex1mtERJSckAIaG2 | Fix Identified Issues | 10. Testing and Validation |  | Completed | Medium | MIURANGA W A R it22209320 | MIURANGA W A R it22209320 | 2026-10-13 |  |  |  | false | 2026-10-13 | MIURANGA W A R it22209320 |  |  |  | Corrected issues identified during testing.
2qCeqWKVX0SyO9jZo3Mv5skAEMaC | Review PP2 Requirements | 12. PP2 — Progress Presentation 2 |  | Completed | Medium | MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 |  |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
R_2d7AMArU-v1PRx5Vw4bMkAFq3m | Review Individual Component Progress | 12. PP2 — Progress Presentation 2 |  | Completed | Medium | MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 |  |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986
oZ0PelAqFkOqE-zphNWD48kAIPBf | Update System Implementation | 12. PP2 — Progress Presentation 2 |  | Completed | Medium | MIURANGA W A R it22209320 | GUNASEKARA L.M.N.P it22267986 | 2026-10-13 |  |  |  | false | 2026-10-13 | GUNASEKARA L.M.N.P it22267986

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
dGQX8oSgZUC1UDoteFlAockALZ8Q | Report monthly status | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Not started | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-10-08 |  |  | true
0jD4mQMw9UyesHKEPM8ilckAKh3G | Report monthly status | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-09-08 |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
eQO25QVO_kqGm47cxW_r9ckABNmU | Report monthly status | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 | 2026-08-08 |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
Yf4OssUZzUuRY-M_RM_cHskAMa7l | Report monthly status | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 | 2026-07-08 |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318
1HB9ntvkqk-8_R2RheSN3MkAOUd6 | Report monthly status | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-06-08 |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318
MIYmCcyhgUWZ_pWeBMlgvskAH7SA | Report monthly status | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-04-29 | 2026-06-26 |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
u0fgWxTZPkGXq-Z2Wbz-pskAFPZi | Summarize project results and lessons learned | aAwz6MsALEC-75Q4aOU20MkAILZ8 |  | Completed | Medium |  | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-04-29 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318
9YcC9HcqI0WKWk7AvggylckAI0D3 | Conduct team performance reviews | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Not started | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 | 2030-09-08 |  |  | false
Vh007uk9yE-xTElFZ7dT8skADENp | Conduct team performance reviews | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 | 2026-07-18 |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318
vfeXmboQ_UamovDn-RXJx8kAGdgB | Conduct team performance reviews | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2027-09-08 |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318
9sh_lIm0MU-OBCMeUkpowckAANkt | Conduct team performance reviews | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-09-08 |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
ijtAq0pG6ESFnPlhdttNQMkAPIAD | Conduct team performance reviews | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-04-29 | 2026-09-26 |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
QVfw8Kn48U22K9u248gidckAH_v3 | Research Topic Finalization | dvst0mCQVEa9BJoQDB5-fskAAyXz |  | Completed | Important | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2025-11-01 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Finalize research title Confirm group members Confirm supervisor Prepare problem statement
hWBjiXu5kkCFqbSJffT7FMkAC66p | Research Proposal Creation | dvst0mCQVEa9BJoQDB5-fskAAyXz |  | Completed | Important | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-02-14 | 2026-02-12 |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Identify research objectives Conduct initial literature review Identify research gapPrepare proposed solution Prepare initial project documentation
b1T4wnoEGEqrwPHy-oPHxMkAEdyW | Dataset Collection | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Urgent | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-04-01 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Tea disease dataset collection Tea grading dataset collection Weather dataset collection Labor management Health Data collection
GB5dCDapvkyIROE1SJuYFMkAJraN | System Planning and Setup | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-04-10 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318
Jvs2vxKahUinnAMg-cKyXMkAHqQC | Create GitHub repository | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-04-11 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318
cUfng4-1oUuA4f7Yeb99vskALXH4 | AI Model Development - Tea Disease Detection System | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Important | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-04-17 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | CNN implementation YOLO Development Image preprocessing Train disease detection model Accuracy testingF1 score evaluation Prediction testing Model optimization
NvFxzavu4ECGmgkCD4x_1skALQ7k | Literature Review | dvst0mCQVEa9BJoQDB5-fskAAyXz |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-02-19 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Collect research papers Study tea industry problem Identify research gap Prepare references
diJTncqHb0WwAC2Q8TD9VckAHZ5- | UI Wireframe Design | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 | 2026-04-19 |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Create dashboard wireframe Design login page Design analytics pages Review UI structure
0c49YPI27kOpZ_Uhdjs_2MkAEtE8 | Frontend Project Setup | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 | 2026-04-21 |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Setup React projectInstall dependencies Configure Tailwind CSS Setup folder structure
Fy7YaYKT1EqXjeV51FRGm8kAJcNe | Backend Project Setup | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Setup Node.js backend Configure Express server Setup API structure Configure middleware
ulxL1inMukiUTudFyfLEAskAOLUA | Database Configuration | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Setup MongoDBConfigure database connection Create collectionsTest database operations
4gajoxcfPk6snQlmO6TjeckABVz6 | Authentication System Setup | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Setup JWT authentication Configure login system Configure register system Test authentication APIs
D7KmFTeapUipd4v7uW_1mckAIe3y | Train ML Model | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Train tea disease detection modelOptimize CNN and YOLO models Evaluate model accuracy Improve F1 Score
mAwHDgH6yEOg46Y_JngiA8kAMJ-D | Backend Connection | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connect AI model with backend Configure FastAPI endpoints Connect MongoDB Test API responses
3PpHaS6qyEuTKIy8Bf7P4ckACWpW | Frontend Connection | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connect frontend image upload Display prediction results Add confidence scores Test frontend integration
iJLIr-C7UESXqOS5lNbhSckAOl-7 | Tea Leaf & Non-Tea Leaf Identification | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Detect tea leaf images Identify non-tea leaf images Improve classification accuracy Test prediction outputs
2HpaJRldo0eF083eD2dcF8kAM7X5 | YOLO Integration | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connect YOLO model Configure object detection Detect tea diseases using YOLO Test live prediction system
65iayVmXDkGqqFO9wvQoSMkACwB0 | PP1 Presentation Create | aAwz6MsALEC-75Q4aOU20MkAILZ8 |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318
231PV_EWdUibOZj_7qPSN8kAOCx5 | Check List 1 README Github | aAwz6MsALEC-75Q4aOU20MkAILZ8 |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318
RVqjqBkD60iB-4cCLino3ckAJLWV | PP1 Presentation | aAwz6MsALEC-75Q4aOU20MkAILZ8 |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318
4z8vJqCdnEGtG9q6p4T-lskAJgji | Disease Detection System | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Detect tea leaf diseasesImprove disease prediction Add disease confidence scoresOptimize disease classification
B3z-QXxT6UGWEy7RNMF4PskABIth | Full System Integration | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Integrate frontend and backendIntegrate AI prediction system Test complete workflow Fix integration issues
oAMlPowAKEe_xnpg2Rj0QckAKG5u | Labor Management and Welfare Planning | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Analyze labor management and worker welfare requirements Design AI-based workforce management workflow Identify worker monitoring and task allocation features Prepare system planning documentation
UsEIvuAheU2rTL6LwfhOvMkAIT6y | Worker Registration and Monitoring | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Design worker management system Create worker data structures and monitoring workflow Implement worker profile and status management Test worker management functionality
__lyi8NTY0u7dMVr-YTkhMkALGwf | AI-Based Health Risk Prediction | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Integrate worker health prediction model Process manually entered Heart Rate and SpO₂ health data Generate worker health risk predictions Test prediction workflow and model responses
MfzOHHFlkkuPJpomC6yU1ckAP-Se | Worker Registration and Monitoring | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-05-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Design worker management system Create worker data structures and monitoring workflow Implement worker profile and status management Test worker management functionality
kswIc-pQz0KhugRirV8rPMkAESnW | Smart Task Allocation System | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Develop AI-based task allocation logic Create risk-based task recommendation process Assign suitable tasks according to worker health condition and skill category Improve workforce allocation efficiency
EKJrK6-gwE2m4BJU_cPk9MkAD9Hk | Backend and Database Integration | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connect labor management module with backend Configure MongoDB collections and APIs Process manual health data inputs Verify backend communication and database operations
e2c456CRqE-lo4ye7gv1wMkABz2P | Frontend Integration and Dashboard | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connect labor management frontend dashboard Add worker monitoring and task allocation UI Display worker health predictions and analytics Test frontend workflow and user interactions
28S1cp7gZ0qC7IdRvYWoTckAJbUa | Future IoT Integration Planning | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-05-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Plan real-time IoT device integration for health monitoring Prepare system workflow for automated data collection Design future real-time monitoring process
FFY07VazPUynEmV6owPbbMkALF2n | Conduct Initial Research Meeting | dvst0mCQVEa9BJoQDB5-fskAAyXz |  | Completed | Urgent | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  | 2026-02-24 |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Discussed the research idea, project scope, and responsibilities among team members.
5D7b3CnXo0--E9QX3crzSMkAMvij | Identify Research Gap | dvst0mCQVEa9BJoQDB5-fskAAyXz |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  | 2026-02-13 |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Identified areas where existing tea estate management approaches could be improved.
8P82YWpsQUeiHRazsCl-bckAHXnI | Discuss Proposal with Supervisor | dvst0mCQVEa9BJoQDB5-fskAAyXz |  | Completed | Medium |  | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318
0wyngspXmUCbNpt21vbSq8kAKQXv | Identify Dataset Sources | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-03-31 | 2026-03-01 |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Identified relevant data sources for disease detection, labour management, weather intelligence and tea grading. Copy task and note
uso7or0MbUKlXlwZSrDp4skAJL_H | Prepare System Design Diagrams | lX1P0OXiBke2W9yzE0jfkckAA4tK |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-03-31 | 2026-03-09 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Prepared worker-related data for labour management and health prediction. Copy task and note
hRB3N5j3jU6V4gTeezcRZ8kAKTGS | Create Dashboard Layout | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-10-10 | 2026-04-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Prepared the shared dashboard layout for the integrated system. Copy task and note
rrlrj6XfVE28-W3hWm3I_ckAIAwT | Test Frontend and Backend Connection | SLCqBrJRIUqx6wTnnkdT9ckACt2p |  | Completed | Important | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-04-15 | 2026-04-10 |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Checked frontend requests, backend responses and connection behaviour. Copy task and note
sF86Pm2d9UmRf34turONDskAPfw1 | Research Tea Leaf Disease Detection | exf-oJ0JYkq49Rk1557m3ckABS_j |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Reviewed image-based methods for identifying tea leaf diseases. Copy task and note
esgNr9KxPEaRosJSFH_xZskAA2hZ | Research Labour Management Requirements | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Reviewed workforce management and worker welfare challenges in tea estates.
QeHSdyKZIEGlkEROGPg978kADtNr | Prepare Worker Health Dataset | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-03-31 | 2026-03-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Prepared worker health data for the prediction component.
g87yy0ub6EOGN0F5FR8RPskAKQzi | Develop Worker Health Prediction Model | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-04-30 | 2026-03-25 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Developed and evaluated the worker health prediction approach.
kNdA2oBZ9kO-EWEa6I-oAskAKNUx | Develop Worker Profile Management | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-04-15 | 2026-04-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Prepared functionality for managing worker information.
V5PYC2TYCEqpaw5uTIDbM8kAPOvc | Develop Task Allocation Workflow | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-04-30 | 2026-04-21 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Developed the workflow for assigning tasks to workers.
FwxEUA697UCacU_xIRsDl8kAG_Bl | Implement Attendance and Productivity Features | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-06-15 | 2026-06-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Developed attendance and productivity monitoring features.
PeozywJuZkWVKAsZtoN3w8kAKbS3 | Integrate Health Monitoring Data | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-07-20 | 2026-07-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Connected available worker health monitoring data to the module.
4rM_QRf3Qka9EcLT9xH1hckAPYE4 | Test Labour Management Module | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-08-15 | 2026-08-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Tested worker management, task allocation and health prediction functionality.
aZetjI1FTUOCjrdWnOsVoMkAK5Tt | Prepare PP2 Demonstration | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-08-30 | 2026-08-21 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Prepared the labour management demonstration for PP2.
g3mDxw4SsUijdK6JdjiFfMkAGOWF | Update Labour Documentation | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Medium |  | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-10-10 | 2026-09-01 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Updated technical documentation and available testing evidence.
Dc6Vr1SFUkCIBp7g6kkGbckAAz9a | Final Labour Module Verification | hNbmT9nuQ063gevgQGwzOMkAAFbp |  | Completed | Important | b805fe56-c739-4285-9af1-254c9d9c1f08 | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 | 2026-10-14 | 2026-10-10 |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Verify the current module and prepare evidence for the final checklist.
EfsmJTEOjkeTOyrWOXDOt8kAPaSG | Research Weather Intelligence Requirements | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | true | [5 empty] | Identified the weather monitoring and forecasting needs of tea estates.
oye7HXWx202u7ztxhKAuKskADdDi | Collect and Prepare Weather Dataset | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-03-31 | 2026-03-01 |  | true | [5 empty] | Prepared temperature, humidity and rainfall data for model development.
GQvI8HLUVkaPc8XMs1yQzckAOedh | Train Weather Prediction Models | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-04-15 | 2026-04-01 |  | true | [5 empty] | Developed models for weather forecasting and tea disease risk prediction.
qRvE3wll_UuGzGbUD-4IkMkAMk3p | Develop Regional Weather Forecasting | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-05-15 | 2026-05-01 |  | true | [5 empty] | Prepared regional forecasting functionality for supported tea-growing areas.
zDFr1sC2_UGMd0V81IEL08kAJtNU | Develop Weather API | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-06-15 | 2026-06-01 |  | true | [5 empty] | Prepared API endpoints for weather readings and prediction results.
AB_69EkMf02eXH6jEKaNHskAGgUn | Integrate Weather Service | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-06-30 | 2026-06-15 |  | true | [5 empty] | Connected the weather service to the main application.
ZJnv3xHMLUe2ihXYdMQr98kACxOb | Implement Weather Risk Alerts | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-07-30 | 2026-07-01 |  | true | [5 empty] | Implemented alerts for supported weather and disease-risk conditions.
WUOeQUy5r0eGXwl0j3QHf8kAAO90 | Test Weather Predictions | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-07-31 | 2026-07-21 |  | true | [5 empty] | Checked forecast outputs and available prediction results.
1lkiVH_ouk2Y_2cURT6_8ckAHckI | Prepare PP2 Demonstration | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-08-20 | 2026-08-01 |  | true | [5 empty] | Prepared the weather intelligence demonstration for PP2.
ehy5WDxXNUGUQhk-eaPul8kAKKIk | Update Weather Documentation | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-09-16 | 2026-09-01 |  | true | [5 empty] | Updated implementation details and supporting evidence.
Q68Lh8WYLUu6XvQJsaPrtckAOhhI | Final Weather Module Verification | J2VNO2x4mkO68A1MyT46ockANUaJ |  | Not started | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-10-21 | 2026-10-01 |  | false | [5 empty] | Verify current weather functionality and prepare final checklist evidence.
SL_NArCGMUKcWXfqPHXtgskALqTt | Research Tea Grading Requirements | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-02-28 | 2026-02-09 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Reviewed the requirements for automated tea quality grading.
nc5KMuZvGUypP1_25jG_C8kAGHus | Prepare Tea Grading Dataset | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-03-15 | 2026-03-01 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Organized tea sample images and the supported grade categories.
i1cGSsbcA0OImT4s6KN-lckANDgB | Preprocess Tea Images | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-04-15 | 2026-04-01 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Prepared tea images for model training and evaluation.
ghpkzRLOKU6IjfqseDjckMkAKd9H | Train Tea Grading Model | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-04-30 | 2026-04-15 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Trained the selected deep learning model for tea grading.
wLIxLsxyO0Wf0aEMjgluHMkANugB | Evaluate Grading Model | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-05-30 | 2026-05-16 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Evaluated grading predictions using the available test data.
UnGIPv2KgUadE26sV9v6GckAIEUH | Deploy Grading Model | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-06-15 | 2026-06-01 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Configured access to the grading inference service.
yX-XQDAVSEKTfrnGq5Aiu8kAHGNl | Prepare PP2 Demonstration | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-10-31 | 2026-08-11 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Prepared the tea grading demonstration for PP2.
0uf84wuJR0Wu5L_IxUzkd8kAAtY9 | Update Grading Documentation | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  | 2026-09-01 |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Updated implementation details and available test evidence.
0ulLgPowT02i0xoliTmKN8kAArWo | Final Grading Module Verification | VKNLfQJYBEOnHD7sHBkqcskAFD6m |  | In progress | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 | 2026-10-19 | 2026-10-01 |  | false | [5 empty] | Verify current grading functionality and prepare final checklist evidence.
Btb1AWF_0U2oZFtdVkhk_8kAFk3W | Prepare Model Training Environment | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Configured the required environment and libraries for model training.
hXpM9_zp-U-ZaL37-MUsXckAAUw1 | Preprocess Training Data | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Prepared training data for use by the selected models.
0e-rW83XdkyjAMKZ0C4M9MkAIr3r | Split Training and Validation Data | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Divided available data for training and model evaluation.
GdhDrvU-0UWv-dGAwq7pJ8kAFroe | Train Component Models | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Trained the machine learning models for the relevant components.
r-9BWDRDv0qXHKo9637XiskAJ1Ie | Tune Model Parameters | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Adjusted model parameters to investigate performance improvements.
Qh8JsE6gs0WK4xxLirr6sMkAAFuH | Evaluate Model Performance | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Evaluated models using appropriate metrics and test data.
T2TpWz-nEUaaiN5V7BoJ5MkAPG_j | Deploy Model APIs | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Configured API access to the deployed models.
KuzyE9O9JEGp-86WP4Df6ckAJjrX | Test Model Predictions | O_vTKFHlE0OYDdbL4J7NaskAA-gB |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | e613108c-2703-498c-a0a9-b95cb2a7749f | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Tested model outputs using suitable input samples.
eZ2ohrMBuU2W9K_W8dybM8kAN_a3 | Integrate Disease Detection Module | DjbAKbWOgUKehVHj_Zx6CMkAB9sr |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connected the disease detection component to the main system.
b_L7h-WbbUqcMnlfFgLHJMkANXTi | Integrate Labour Management Module | DjbAKbWOgUKehVHj_Zx6CMkAB9sr |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Connected the labour management component to the main system.
qaxr_QSU5k6cSEKSGtnPqMkAHV4s | Integrate Weather Module | DjbAKbWOgUKehVHj_Zx6CMkAB9sr |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Connected the weather intelligence component to the main system.
85aJSc4spUKmwEbEn2OfGMkAG6bm | Integrate Tea Grading Module | DjbAKbWOgUKehVHj_Zx6CMkAB9sr |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Connected the tea grading component to the main system.
BRAZAWWGxkKtn1mR1BpzBskADm0s | Verify Frontend and Backend Communication | DjbAKbWOgUKehVHj_Zx6CMkAB9sr |  | Completed | Important | 957e5fe0-45cc-44f4-8728-926a5d59bc5f;e613108c-2703-498c-a0a9-b95cb2a7749f;b805fe56-c739-4285-9af1-254c9d9c1f08;6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Checked communication between the user interface and backend services.
xWRBlPjLA0CGjqaON4NB88kAOwN- | Prepare Functional Test Cases | qFJ4s4oWwkaLytxCqzL5YckAFo4L |  | Completed | Medium | e613108c-2703-498c-a0a9-b95cb2a7749f | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | e613108c-2703-498c-a0a9-b95cb2a7749f |  |  |  | Prepared test cases for the main system functions.
qriOGYtvCkKVZFZWMkeEUMkADzIg | Test Individual Components | qFJ4s4oWwkaLytxCqzL5YckAFo4L |  | Completed | Medium | b805fe56-c739-4285-9af1-254c9d9c1f08 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08 |  |  |  | Tested the functions of each individual component.
YN0n5j77kEinRGbdlRUHockALMST | Test Valid and Invalid Inputs | qFJ4s4oWwkaLytxCqzL5YckAFo4L |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Checked system behaviour with valid and invalid inputs.
BOU1W79_VkOMe2Wu5EpkjskAMJDm | Verify ML Model Predictions | qFJ4s4oWwkaLytxCqzL5YckAFo4L |  | Completed | Medium | 957e5fe0-45cc-44f4-8728-926a5d59bc5f | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Checked model outputs against the available test samples.
tkfVjlSHBk2Qex1mtERJSckAIaG2 | Fix Identified Issues | qFJ4s4oWwkaLytxCqzL5YckAFo4L |  | Completed | Medium | 6066b4cd-9636-490f-9542-ffde01827318 | 6066b4cd-9636-490f-9542-ffde01827318 | 2026-10-13 |  |  |  | false | 2026-10-13 | 6066b4cd-9636-490f-9542-ffde01827318 |  |  |  | Corrected issues identified during testing.
2qCeqWKVX0SyO9jZo3Mv5skAEMaC | Review PP2 Requirements | VyByn4hBZkmJHDdEjjm3YskAKehd |  | Completed | Medium |  | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 |  |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
R_2d7AMArU-v1PRx5Vw4bMkAFq3m | Review Individual Component Progress | VyByn4hBZkmJHDdEjjm3YskAKehd |  | Completed | Medium |  | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 |  |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08
oZ0PelAqFkOqE-zphNWD48kAIPBf | Update System Implementation | VyByn4hBZkmJHDdEjjm3YskAKehd |  | Completed | Medium |  | b805fe56-c739-4285-9af1-254c9d9c1f08 | 2026-10-13 |  |  |  | false | 2026-10-13 | b805fe56-c739-4285-9af1-254c9d9c1f08

## Buckets
Bucket ID | Bucket Name
dvst0mCQVEa9BJoQDB5-fskAAyXz | 1. Project Initialization
lX1P0OXiBke2W9yzE0jfkckAA4tK | 2. System Planning & Dataset Preparation
SLCqBrJRIUqx6wTnnkdT9ckACt2p | 3. Frontend and Backend Setup
exf-oJ0JYkq49Rk1557m3ckABS_j | 4. System Development — Disease Detection
hNbmT9nuQ063gevgQGwzOMkAAFbp | 5. System Development — Labour Management
J2VNO2x4mkO68A1MyT46ockANUaJ | 6. System Development — Weather Intelligence
VKNLfQJYBEOnHD7sHBkqcskAFD6m | 7. System Development — Tea Sorting & Grading
O_vTKFHlE0OYDdbL4J7NaskAA-gB | 8. Machine Learning Model Development
DjbAKbWOgUKehVHj_Zx6CMkAB9sr | 9. System Integration
qFJ4s4oWwkaLytxCqzL5YckAFo4L | 10. Testing and Validation
aAwz6MsALEC-75Q4aOU20MkAILZ8 | 11. PP1 — Progress Presentation 1
VyByn4hBZkmJHDdEjjm3YskAKehd | 12. PP2 — Progress Presentation 2

## Users
User ID | User Name | Email
e613108c-2703-498c-a0a9-b95cb2a7749f | PATHIRANA I M it22282668 | it22282668@my.sliit.lk
b805fe56-c739-4285-9af1-254c9d9c1f08 | GUNASEKARA L.M.N.P it22267986 | it22267986@my.sliit.lk
6066b4cd-9636-490f-9542-ffde01827318 | MIURANGA W A R it22209320 | it22209320@my.sliit.lk
957e5fe0-45cc-44f4-8728-926a5d59bc5f | GUNASEKARA G N D it22279620 | it22279620@my.sliit.lk